| Intention statements: To integrate the Forest School ethos into our curriculum. To set up and maintain a sustainable small woodland on the school site. To ensure the land is managed and looked after- teaching our children skills and responsibilities towards our earth and its future. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Phase | Action | Persons responsible | Timescale | Funding | Evaluation/next steps |
| Phase 1- | A. Hunter and S. Llyod to gain Level 3 Forest school qualification. | A. Hunter K.Okane | 2021-22 | School budget |  |
| Phase 2 | EYFS to begin forest school sessions one day a week during Spring 2-Summer 2 | A.Hunter | 2021-22 | Small budget allocation for weekly resources needed |  |
| Phase 3 | Source waterproof clothing and hats for all children. | A.Hunter | 2021-22 | Parent donation £700 |  |
| Phase 4 | Develop a resource list for each area and purchase resources | A.Hunter | 2021-22 | School budget |  |
| Phase 5 | Order hedgerows and new trees for planting with the school community. | A.Hunter | 2021-22 | Woodland trust provided free trees. |  |
| Phase 6 | Develop a woodland area on school grounds- to involve parents and children. Create a fire circle and wigloo, plant new trees due to arrive in May 2022 | A.Hunter | 2021-22 |  |  |
| Phase 7 | Create area for storage of forest school equipment- shed n forest school site. | A.Hunter | 2022-23 | Approx £500 |  |
| Phase 8 | Work as a school to develop a pond site on the school grounds. Encourage parent working parties to assist in creating and maintaining a pond. | A.Hunter K.Okane | 2022-23 |  |  |
| Phase 9 | Discuss with parents, children, staff and governors ways to separate forest school from the rest of the school grounds, fencing to be considered. | A.Hunter K.Okane | 2022-23 | Source grants or other sources of funding. |  |
| Phase 10 | Forest school INSET session to be planned for staff and governors. | A.Hunter | 2022-23 |  |  |
| Phase 11 | For two other members of staff to be trained up to Level 3 | K.Okane | 2022-23 |  |  |
| Phase 12 | Integrate forest school sessions into every year group | K.Okane | 2022-23 |  |  |
| Phase 13 | All teaching staff to hold a level 3 Forest school qualification | K.Okane | 2023-24 |  |  |